## Slide 1
Regional Communications System
San Diego County & Imperial County
1980's
Most Public Safety Communications in San Diego and Imperial Counties were on VHF (150-160 MHz)
All Operations were Conventional
1980's
1992
1993-1995
1998 + 15 yrs
2009, 2010, 2011
1998 + 15 yrs
Motorola SmartZone- Analog and Digital talkgroups, Digital Encryption capable, 60+ Microwave repeater sites (both counties)
Projected service life: 15 years
1993-1995
Consultant recommendation to develop a trunked Regional Communications network was made to the San Diego County Board of Supervisors
1995 – Budget established for infrastructure, site development, user equipment and a new Dispatch Center/Emergency Operations Center
2009, 2010, 2011
2009 Engaged Consultant
2010,2011 Established Baseline and Design alternative
1992
San Diego Board of Supervisors directed the CAO to develop plans for a replacement Public Safety Radio System in San Diego County
2013
2014-2015
2016
2017
2018
2019
2013
Extended 1995 Partnership agreement, replaced original core with P25 core
2014-2015
Microwave backbone replaced
2015 Replacement network proposals released
2016
Motorola Solutions, Inc. contract awarded; Design review
2017
Factory Acceptance tests
2018
March Installation complete
June Optimization complete
2019
Next Generation System Contract
Field Functional Acceptance testing
User migration completed
Final system acceptance
System upgrades every 2 years, for 10 years